## Implementation_Back Out Plan
Change Management Implementation Plan
Section A: General Information:
Start Date and Time: | 2018-10-04 08:30 | Do not edit these cells. Cells will auto-populate. <--------------- This information should match RFC form.
End Date and Time: | 2018-10-08 10:05
Total Duration | 1900-01-03 01:35
RFC # and Application/ System Name: | CHG - STS Anesthesia Registry - UAT to Prod
Change Owner: | Douglas Ryba
Technical Bridge Line: | n/a
Clinical Bridge Line: | n/a
Section B: Communication Plan Details - If applicable (if not applicable, hide section)
Row # | Start Time | End Time | Implementer |  | Tasks | Task Complete
1 |  |  | Service Desk |  | Post downtime message on Service Desk Upcoming Planned Downtimes blog
2 |  |  | Service Desk |  | Before Event - send clinical pages (Ascom and Clinical 24/7) "Insert text here"
3 |  |  | Service Desk |  | At completion - send clinical pages (Ascom and Clinical 24/7) "Insert text here"
4 |  |  | Service Desk |  | Mark Service Desk blog posting as COMPLETE
Section C: Implementation Plan Details
Row # | Start Time | End Time | Duration (minutes) | Implementer | Tasks | Task Complete
1 | 2018-10-04 08:30 | 2018-10-04 08:35 | 5 | Douglas Ryba | Contact Service Desk that change has begun Mon-Fri 24/5 – Hotline – 267-426-0499 Weekend - Friday 11 pm to Monday 7 am - Cell – 215-407-4676
2 | 2018-10-04 08:35 | 2018-10-04 08:40 | 5 | Douglas Ryba | Verify if the Change is approved
3 | 2018-10-04 08:40 | 2018-10-04 08:45 | 5 | Douglas Ryba | Verify CDW daily etl is complete.
4 | 2018-10-04 08:45 | 2018-10-04 08:50 | 5 | Douglas Ryba | Go/ No Go Decision (Move as appropriate)
5 | 2018-10-04 08:50 | 2018-10-04 08:55 | 5 | Douglas Ryba | Point Targets to Centripetus Prod (SQLS_Centripetus_CCIS) Check in all components
6 | 2018-10-04 08:55 | 2018-10-04 09:10 | 15 | Douglas Ryba | Using PSQLA012/Centripetus Create new STG tables - Execute DDL by running CARDIOACCESS_CCAS_DDL_v2.sql Add Triggers to new tables
7 | 2018-10-04 09:10 | 2018-10-04 09:25 | 15 | Yuliya Chudnovskaya | Using CHOPDW/CDW_STG Create new STG tables - Execute DDL by running S_CDW_CCAS_ANESTHESIA_DDL.SQL
8 | 2018-10-04 09:25 | 2018-10-04 09:55 | 30 | Ivonne McGlynn | Promote workflow Wk_STG_load_STS_CCAS_REGISTRY from EAR_TST.CCIS_PDA TO INFMT_PRD.CCIS_PDA and all corresponding components
9 | 2018-10-04 09:55 | 2018-10-04 10:05 | 10 | Ivonne McGlynn | Execute workflow in PRD
10 | 2018-10-04 10:05 | 2018-10-08 10:05 | 5760 | Douglas Ryba | Data Validation
11 | 2018-10-08 10:05 | 2018-10-08 10:05 | 0 |  | Contact Service Desk that change has completed Mon-Fri 24/5 – Hotline – 267-426-0499 Weekend - Friday 11 pm to Monday 7 am - Cell – 215-407-4676
12 | 2018-10-08 10:05 | 2018-10-08 10:05 | 0 |  | DO NOT EDIT/DELETE THIS ROW
Total Duration |  |  | 97:35
Section D: Back Out Plan Tasks
Row # | Start Time | End Time | Duration (Minutes) | Implementer | Tasks | Task Complete
1 | 2018-10-04 09:50 | 2018-10-04 09:55 | 5 | Douglas Ryba | Contact Manager that Back Out Plan is being invoked
2 | 2018-10-04 09:55 | 2018-10-04 10:00 | 5 | Fernando Gonzalez | Manager Contact Service Desk that Back Out Plan is being invoked Mon-Fri 24/5 – Hotline – 267-426-0499 Weekend - Friday 11 pm to Monday 7 am - Cell – 215-407-4676
3 | 2018-10-04 10:00 | 2018-10-04 10:10 | 10 | Yuliya Chudnovskaya | Drop the tables created in DDL
4 | 2018-10-04 10:10 | 2018-10-04 10:25 | 15 | Ivonne McGlynn | Delete the workflow and all components
5 | 2018-10-04 10:25 | 2018-10-04 10:25 | 0
6 | 2018-10-04 10:25 | 2018-10-04 10:25 | 0 |  | DO NOT EDIT/DELETE THIS ROW
Total Duration |  |  | 0:35
Section E: Key Contacts
Contact name | Contact information
Fernando Gonzalez | 267-426-0686
Douglas Ryba | 267-426-0334
Ivonne McGlynn | 267-426-0362
Yuliya Chudnovskaya | 267-426-1798
Formulas:
End Time = [Start Time]+([Implementer]/1440)
Start Time = OFFSET([Start Time],-1,1)
Note on B18: Edit the Start time using the following format: MM/DD/YYYY HH:MM (24hr)
Note on D18: Enter duration of task in # of minutes
Note on B33: Edit the Start time using the following format: MM/DD/YYYY HH:MM (24hr) Start time should be the end time of first go/no go decision
Note on D33: Enter duration of task in # of minutes

## Implementation_Without Formulas
Change Management Implementation Plan
Section A: General Information:
Start Date and Time: | 2017-01-01 08:00 | Do not edit these cells <--------------- This information should match RFC form
End Date and Time: | 2017-01-01 08:00
Total Duration | 0
RFC # and Application/ System Name:
Change Owner:
Technical Bridge Line:
Clinical Bridge Line:
Section B: Communication Plan Details - If applicable (if not applicable, hide section)
Row # | Start Time | End Time | Implementer |  | Tasks | Task Complete
1 |  |  | Service Desk |  | Send Support Center Message via IS Broadcast (Tuesday and/or Thursday)
2 |  |  | Service Desk |  | Send Support Center Message - event to begin Update intranet (if applicable)
3 |  |  | Service Desk |  | Before Event - send clinical pages (Xtend and Ascom) "Insert text here"
4 |  |  | Service Desk |  | At completion - send clinical pages (Xtend and Ascom) "Insert text here"
5 |  |  | Service Desk |  | Send Support Center Message - event complete Update intranet (if applicable)
Section C: Implementation Plan Details
Row # | Start Time | End Time | Duration (minutes) | Implementer | Tasks | Task Complete
1 | 2017-01-01 08:00 |  |  |  | Contact Service Desk that change has begun Mon-Fri 24/7 – Hotline – 267-426-0499 Mon-Fri 9pm-7:30a/Weekends-Off Hours Cell – 215-407-4676
2
3
4 |  |  |  |  | Go/ No Go Decision (Move as appropriate)
5
6
7
8
9
10 |  | 2017-01-01 08:00 |  |  | Contact Service Desk that change has completed Mon-Fri 24/7 – Hotline – 267-426-0499 Mon-Fri 9pm-7:30a/Weekends-Off Hours Cell – 215-407-4676
Total Duration |  |  | 0:00
Section D: Back Out Plan Tasks
Row # | Start Time | End Time | Duration (Minutes) | Implementer | Tasks | Task Complete
1 | 2017-01-01 08:00 |  |  |  | Contact Manager that Back Out Plan is being invoked
2 |  |  |  |  | Manager Contact Service Desk that Back Out Plan is being invoked Mon-Fri 24/7 – Hotline – 267-426-0499 Mon-Fri 9pm-7:30a/Weekends-Off Hours Cell – 215-407-4676
3
4
5 |  | 2017-01-01 08:00
Total Duration |  |  | 0:00
Section E: Key Contacts
Contact name | Contact information
Edit the Start time using the following format:
MM/DD/YYYY HH:MM (24hr)
Note on B19: Edit the Start time using the following format: MM/DD/YYYY HH:MM (24hr)
Note on D19: Enter duration of task in # of minutes
Note on B32: Edit the Start time using the following format: MM/DD/YYYY HH:MM (24hr) Start time should be the end time of first go/no go decision
Note on D32: Enter duration of task in # of minutes